## Read Me
SafeX Solutions — Vulnerability Findings & Remediation Tracker
Built for: Process-Improvement Proposal — Mini-Project, Group 40 (Ayza Waseem)
WHAT THIS IS
A lightweight, no-new-software tracker that replaces the current practice of sending vulnerability-assessment findings to clients as a static PDF/email with no shared, living record of remediation status.
HOW TO USE IT
1. Open the 'Findings Log' tab. Each row is one vulnerability finding.
2. Add a new finding below the last row. Fill in the columns shown in BLUE font — these are the only cells you type into.
3. Columns in BLACK font calculate themselves (SLA due date, days remaining/overdue) — never type into these.
4. Pick Severity and Status from the dropdown lists provided in those cells.
5. Open the 'Dashboard' tab to see live totals and the overdue count update automatically.
6. The 'SLA Reference' tab holds the remediation-deadline policy per severity. Change the days there if your team's policy differs — every finding's due date updates automatically.
COLOUR LEGEND
Blue text = type here (inputs)
Black text = formula, do not overwrite
Red row = overdue and still open
Yellow row = due within 2 days
Green row = resolved / verified closed
WHY THIS MATTERS
Full reasoning, current-state analysis, and expected impact are in the accompanying document 'Process-Improvement Proposal.docx'. This workbook is the working module referenced there.

## SLA Reference
Severity | SLA (Business Days) | Description
Critical | 3 | Actively exploitable / severe business impact. Remediate immediately.
High | 7 | Significant risk of exploitation. Remediate within one week.
Medium | 30 | Moderate risk. Remediate within the current sprint/month.
Low | 90 | Minor risk. Remediate during the next scheduled maintenance cycle.
Note: SLA days are business-policy inputs — edit freely; every finding's due date recalculates automatically.

## Findings Log
Finding ID | Client | Asset / System | Vulnerability | Severity | CVSS | Date Identified | SLA (Days) | Due Date | Recommended Fix | Owner | Status | Date Resolved | Days Remaining / Overdue
VF-0001 | Client A - Retail Co | Customer web portal | SQL injection on login form | Critical | 9.8 | 2026-07-11 | 3 | 2026-07-14 | Patch input validation; deploy WAF rule | Dev Team - S. Khan | Open |  | -2
VF-0002 | Client A - Retail Co | Admin panel | Default admin credentials in use | Critical | 9.1 | 2026-07-15 | 3 | 2026-07-18 | Force password reset; enforce MFA | Security Team - A. Raza | In Progress |  | 2
VF-0003 | Client B - Fintech Co | API gateway | Missing rate limiting on auth endpoint | High | 7.5 | 2026-07-07 | 7 | 2026-07-14 | Add rate limiting + lockout policy | Dev Team - M. Ali | Open |  | -2
VF-0004 | Client B - Fintech Co | Payment DB server | Outdated TLS version (TLS 1.0) | High | 7 | 2026-07-14 | 7 | 2026-07-21 | Upgrade to TLS 1.2+; disable legacy ciphers | Infra Team - H. Baig | In Progress |  | 5
VF-0005 | Client C - Retail Co | Marketing website | Outdated WordPress plugin (XSS) | Medium | 5.4 | 2026-06-26 | 30 | 2026-07-26 | Update plugin; add CSP header | Dev Team - S. Khan | Resolved | 2026-07-14 | Closed
VF-0006 | Client C - Retail Co | Cloud storage | Publicly readable S3 bucket | Critical | 8.6 | 2026-07-12 | 3 | 2026-07-15 | Restrict bucket policy; audit access logs | Infra Team - H. Baig | Open |  | -1
VF-0007 | Client D - Logistics Co | Employee portal | No account lockout after failed logins | Medium | 5 | 2026-07-06 | 30 | 2026-08-05 | Add lockout after 5 attempts | Dev Team - M. Ali | Open |  | 20
VF-0008 | Client D - Logistics Co | Internal network | Unpatched CMS (known CVE) | High | 8.2 | 2026-07-01 | 7 | 2026-07-08 | Apply vendor security patch | Infra Team - A. Raza | Verified Closed | 2026-07-10 | Closed
VF-0009 | Client E - Fintech Co | Mobile app backend | Sensitive data logged in plaintext | Medium | 6.1 | 2026-07-13 | 30 | 2026-08-12 | Mask PII in logs; rotate exposed keys | Dev Team - S. Khan | Open |  | 27
VF-0010 | Client E - Fintech Co | Corporate VPN | No MFA on VPN access | Low | 4.3 | 2026-07-15 | 90 | 2026-10-13 | Enable MFA for all VPN accounts | Security Team - A. Raza | Open |  | 89
Formulas:
Due Date = [Date Identified]+[SLA (Days)]
Days Remaining / Overdue = IF(OR([Status]="Resolved",[Status]="Verified Closed"),"Closed",[Due Date]-TODAY())

## Dashboard
Vulnerability Remediation Dashboard
Auto-calculated from 'Findings Log'. Updates the moment a new finding is added.
Total Findings | Open | In Progress | Resolved / Closed | Overdue (open + past due)
10 | 6 | 2 | 2 | 3
% of Open Findings Within SLA | 62.5%
Open Findings by Severity
Severity | Count
Critical | 3
High | 2
Medium | 2
Low | 1